|  |  |
| --- | --- |
| enspire_logo_600x187 | **DAU FPD200 Status Update**  **For October, 2011**  **Submitted 14 November, 2011** |

Project Timeline

|  |  |  |
| --- | --- | --- |
| Planning | ~~Kickoff Meeting~~  ~~Enspire Release: PMP~~  ~~DAU Review/Feedback: PMP~~  ~~Enspire Release: Revised PMP~~  ~~DAU Review/Feedback: Revised PMP~~ | ~~16 August, 2011~~  ~~29 August, 2011~~  ~~8 September, 2011~~  ~~13 September, 2011~~  ~~16 September, 2011~~ |
| Design | ~~Enspire Release: CDD~~  ~~DAU Review/Feedback: CDD~~  ~~Enspire Release: Script/Styleboards~~  ~~DAU Review/Feedback: Script/Styleboards~~ | ~~15 September, 2011~~  ~~21 September, 2011~~  ~~20 October, 2011~~  ~~28 October, 2011~~ |
| *The dates below are listed as they were last approved, though we have abandoned these dates in order to revisit project scope.* | | |
| Prototype | Enspire Release: Prototype  DAU Review/Feedback: Prototype | 11 November, 2011  18 November, 2011 |
| Alpha | Enspire Release: Programmed Lessons  DAU Review/Feedback: Programmed Lessons | 8 December, 2011  15 December, 2011 |
| Beta | Enspire Release: Beta (Pilot-Ready)  DAU-Hosted Pilot Test  DAU Review/Feedback: Pilot | 12 January, 2012  23-27 January, 2012  3 February, 2012 |
| Final | Enspire Release: Final Candidate  DAU Final Approval/Acceptance  Enspire Release: Maintenance Plan | 16 February, 2012  23 February, 2012  29 February, 2012 |

October Accomplishments

* Delivered script/styleboards for Lesson 2
* Began discussing DAU’s feedback on Lesson 2
* Received a completed POI and ISP for a sample course, CON090
* Modified the two POs with GDIT to move the balance of Phase 1 hours into Phase 2

Outstanding Issues/Risks

* *Scope*. We're concerned about the difficulty we've had getting a firm grasp on what will actually be expected of us, and if our current understanding of the scope is accurate, we have an additional concern that this scope would require a time commitment from Debra and/or Sabrina that they are not able to provide.
  + Mitigation strategy: You (Dave) will be meeting with Sylwia to discuss concerns and next steps. Then all of us will reconvene on a call to strategize about whether/how to move forward.