|  |  |
| --- | --- |
| enspire_logo_600x187 | **DAU FPD200 Status Update**  **For December, 2011**  **Submitted 6 January, 2012** |

Project Timeline

|  |  |  |
| --- | --- | --- |
| Planning | ~~Kickoff Meeting~~  ~~Enspire Release: PMP~~  ~~DAU Review/Feedback: PMP~~  ~~Enspire Release: Revised PMP~~  ~~DAU Review/Feedback: Revised PMP~~ | ~~16 August, 2011~~  ~~29 August, 2011~~  ~~8 September, 2011~~  ~~13 September, 2011~~  ~~16 September, 2011~~ |
| Design | ~~Enspire Release: CDD~~  ~~DAU Review/Feedback: CDD~~  ~~Enspire Release: Script/Styleboards~~  ~~DAU Review/Feedback: Script/Styleboards~~ | ~~15 September, 2011~~  ~~21 September, 2011~~  ~~20 October, 2011~~  ~~28 October, 2011~~ |
| *The dates below represent the newly approved timeline for Module 2.* | | |
| Enspire Release: Outline of new content in Participant Guide | | 06 January, 2012 |
| DAU Review/Feedback | | 12 January, 2012 |
| Enspire Release: Three documents 1) 2nd draft of Participant Guide 2) 2nd draft of Quiz A 3) Outline of new case study approach | | 20 January, 2012 |
| DAU Review/Feedback | | 25 January, 2012 |
| Enspire Release: Two sets of documents 1) 1st draft of new case study 2) 2nd draft of Assignment Sheet, Quiz B, IOAP, & CSAP | | 31 January, 2012 |
| DAU Review/Feedback | | 06 February, 2012 |
| Enspire Release: 2nd draft of case study | | 08 February, 2012 |
| DAU Review/Feedback | | 13 February, 2012 |
| Enspire Release: Final draft of all Module 2 | | 15 February, 2012 |

December Accomplishments

* December 1 – received word from DAU of desire to proceed with Module 2 only
* December 1-19 – clarified/confirmed approach
* December 21 – confirmed new schedule

Outstanding Issues/Risks

* Moving goalposts: It’s possible that DAU’s vision for what the product will be become will continue to be organic.
  + Mitigation strategy: The new schedule for Module 2 includes many revisions of each document before it will be considered complete.
* Remainder of the course: It’s unclear whether DAU will be pleased with the result of the reconceived Module 2, and thus would want to continue with the rest of the course.
  + Mitigation strategy: We will continue to do our best to implement the changes that are requested in each review cycle.