|  |  |
| --- | --- |
| enspire_logo_600x187 | **DAU FPD200 Status Update**  **For September, 2011**  **Submitted 7 October, 2011** |

Project Timeline

|  |  |  |
| --- | --- | --- |
| Planning | ~~Kickoff Meeting~~  ~~Enspire Release: PMP~~  ~~DAU Review/Feedback: PMP~~  ~~Enspire Release: Revised PMP~~  ~~DAU Review/Feedback: Revised PMP~~ | ~~16 August, 2011~~  ~~29 August, 2011~~  ~~8 September, 2011~~  ~~13 September, 2011~~  ~~16 September, 2011~~ |
| Design | ~~Enspire Release: CDD~~  ~~DAU Review/Feedback: CDD~~  Enspire Release: Script/Styleboards  DAU Review/Feedback: Script/Styleboards | ~~15 September, 2011~~  ~~21 September, 2011~~  20 October, 2011  28 October, 2011 |
| Prototype | Enspire Release: Prototype  DAU Review/Feedback: Prototype | 11 November, 2011  18 November, 2011 |
| Alpha | Enspire Release: Programmed Lessons  DAU Review/Feedback: Programmed Lessons | 8 December, 2011  15 December, 2011 |
| Beta | Enspire Release: Beta (Pilot-Ready)  DAU-Hosted Pilot Test  DAU Review/Feedback: Pilot | 12 January, 2012  23-27 January, 2012  3 February, 2012 |
| Final | Enspire Release: Final Candidate  DAU Final Approval/Acceptance  Enspire Release: Maintenance Plan | 16 February, 2012  23 February, 2012  29 February, 2012 |

September Accomplishments

* Delivered PMP and CDD, with very favorable responses from DAU regarding the CDD
* Began work on script/styleboards
* Received sample ISP

Outstanding Issues/Risks

* *Insufficient information from DAU about the standard course development process*. The interactive case study that Enspire intends to develop will model the development of a DAU course from start to finish. In the CDD, we described this plan, and indicated that we were still lacking information about this process; all we had received was a finished course, not a description of how it had been developed. As of the end of September, Enspire had not received anything to that effect.
  + Mitigation strategy: Though this Status Report technically only reflects activities in September, Enspire did receive from DAU useful information on 7 October, which should permit us to continue with the development of the script & styleboards.
* *Irregular contact with DAU*. There are three key decision-makers on DAU’s end: Debra, Sabrina, and Sylwia. It has thus far proven difficult to receive information and decisions from DAU, largely because the decisions are shared by multiple people, and each of them has a busy schedule.
  + Mitigation strategy: Dave, if it’s okay with you, I’d like to propose a regular weekly call with everybody. We may not need them every week, but it will be easier to put them on the calendar in advance.