## Sheet1
Sales estimation tool (area in Green) | [15 empty] | Dropdown Data | [5 empty] | Line Items for Proposal (Automatically Generated)
[5 empty] | NewEstimate | [16 empty] | Custom e-learning lasting 75 minutes of learner seat time (or approximately 150 segments)
| Basic estimation parameters | [20 empty] | Level 2 Multimedia: Audiovisual production such as basic animations and some custom-developed images including iconographics, illustrations, and photography.
|  | SOW deliverables |  |  | Entry Field | Amount | Yes/no | [14 empty] | Level 2 Interactivity: Interactive elements are tailored from advanced templates and may include dynamic assessments, drag-and-drop elements, and basic learning games, demonstrations of software, template-based and custom.
|  |  | Concept Doc |  | 1 | 1 |  |  | Pricing Overview | [6 empty] | Concept Doc | [5 empty] | Interactivities included every 5 - 9 segments
|  |  | Design Prototype (Storyboards) |  | 1 | 1 |  |  |  | Price | Margin | $/hour | ($-OOP)/hour |  |  | Prototype | [5 empty] | Audio narration recording, editing, and integration using 3 voice actors in Enspire's in-house recording studio
|  |  | Alpha |  | 1 | 1 |  |  | At Cost | 100442.8169 | 0% | 92.885 | 83.3924 |  |  | Alpha | [5 empty] | Custom music design including intro and outro themes and background music.
|  |  | Are we doing a video? |  | no | no | 0 |  | At Minimum | 111603.1298 | 10% | 103.2056 | 93.713 |  |  | Are we doing a video? | no | yes |  |  |  | Custom sound design including audio feedback and sound effects (for example, button 'clicks' and sounds of machinery in a factory scenario)
[9 empty] | At $95/hr | 102729.8752 | 2.226% | 95 | 85.5074 | [8 empty] | Professional photo shoot at Enspire's in-house studio using a green screen using 6 actors.
|  | Key variables |  |  | Entry Field | Rating | Coefficient |  | Quoted | 111000 | 9.511% | 102.6478 | 93.1552 | [9 empty] | NOTE: If there is a video estimate included that isn't a separate line item, consider adding this text too, "Custom video shoot with advanced features"
|  |  | Segments |  | 150 | 150 | 1.25 | [8 empty] | Segments | [5 empty] | Custom GUI design with advanced features such as bookmarking, glossary, intuitive menu system, volume and navigation controls, resume functionality, and linking to embedded or external resources
|  |  | Content Disarray (1-5) |  | 2 | 2 | 0.54433 |  |  | Predicted | Actual | %Diff |  |  |  | Content Disarray (1-5) | 1 | 2 | 3 | 4 | 5 | Development process deliverables will include 1 concept document and 1 design prototype and 1 alpha stage review
|  |  | Content Difficulty (1-5) |  | 2 | 2 | 1 |  | CT | 386.9051 | 0 | 100% |  |  |  | Content Difficulty (1-5) | 1 | 2 | 3 | 4 | 5 | Full 508 Compliance
|  |  | Visual Media Level (1-3) |  | 2 | 2 | 2 |  | MM | 282.7528 | 0 | 100% |  |  |  | Visual Media Level (1-3) | 1 | 2 | 3 |  |  | LMS Integration Support - Enspire technology works with your LMS administrator to ensure a successful integration
|  |  | Photoshoot |  | yes |  | 1 |  | SVP | 84.75 | 0 | 100% |  |  |  | Phtotoshoot | no | yes
|  |  |  | Talent | 6 |  | 6 |  | PM | 157.0466 | 0 | 100% |  |  |  | Talent | [5 empty] | Multimedia Level Descriptions
|  |  |  | Locations (0=Green screen) | 0 |  | 0 |  | Tech | 113.7262 | 0 | 100% |  |  |  | Locations | [5 empty] | Level 1 Multimedia: Audiovisual production including static illustrations, iconographics, stock photography, and client-provided assets.
|  |  | Interactivity Level (1-3) |  | 2 | 2 | 2.2974 |  | QA | 56.1864 | 0 | 100% |  |  |  | Interactivity Level (1-3) | 1 | 2 | 3 |  |  | Level 2 Multimedia: Audiovisual production such as basic animations and some custom-developed images including iconographics, illustrations, and photography.
|  |  | Interactivity Frequency (1-3) |  | 2 | 2 | 1 |  | Total Hours | 1081.3671 | 0 | 100% |  |  |  | Interactivity Frequency (1-3) | 1 | 2 | 3 |  |  | Level 3 Multimedia: Audiovisual production such as complex animations and a frequent custom developed images including illustrations, iconographics, and photography.
|  |  | GUI (yes/no) |  | yes | yes | 1 |  | Total OOP Exp. | 10265 | - | - | - |  |  | GUI (1=Custom, 0=template) | no | yes |  |  |  | Interactivity Level Descriptions
|  |  | Voice Over (yes/no) |  | yes | yes | 1 | 3-4 main characters with some extra people to interact with | [7 empty] | Voice Over (1=yes, 0=no) | no | yes |  |  |  | Level 1 Interactivity: All interactivities are based on Enspire's interactivity templates (e.g. multiple choice, true/false). The appearance of interactivity templates is aligned with that of the interface and does not vary from instance to instance.
|  |  |  | Additional voice talent | 3 | 3 | 3 | If we could convince the client, something with more MM including silhouette avatars placed in a shoot of the actual DAU campus would be cool, but it would require a different $ | [7 empty] | Additional voice talent | [5 empty] | Level 2 Interactivity: Interactive elements are tailored from advanced templates and may include dynamic assessments, drag-and-drop elements, and basic learning games, demonstrations of software, template-based and custom.
|  |  | Music (yes/no) |  | yes | yes | 1 | About 1.5 hr seat time | [7 empty] | Music (1=yes, 0=no) | no | yes |  |  |  | Level 3 Interactivity: The overall course is typically linear, but the learning experience may be substantially built around advanced non-linear activities such as learning games and simple simulations. Interactivities are mostly based on advanced templates but may include a limited number of entirely custom-designed interactivities such as interactive graphs and spreadsheets.
|  |  | Sound Design |  | yes |  | 1 | [8 empty] | Sound Design | no | yes
|  |  | Client Difficulty (1-5) |  | 3 | 3 | 2.4401 | The price in the proposal will have $11k on top to account for what we would owe UCF | [7 empty] | Client Difficulty (1-5) | 1 | 2 | 3 | 4 | 5
|  |  | Kickoff length |  | 4 | 4 | 4 | [8 empty] | Kickoff length
|  |  | Kickoff Location (1=phone, 2=enspire, 3=client) |  | 1 | 1 | 1 | Includes a Needs Analysis phase -- majority content, some PM | [7 empty] | Kickoff Location (1=phone, 2=enspire, 3=client) | 1 | 2 | 3
|  |  | Special Content Workshop (enter hours here) |  | 0 | 0 | 0 | Now includes travel hours and an expense budget for 3 trips | [7 empty] | Special Content Workshop (enter hours here)
|  |  | Deployment Context (1=No LMS or SCORM Level 1 Support; 2=SCORM Level 2 Support) |  | 2 | 2 | 1 |  | 1. Kickoff, CT and PM, 1 day event, content stay one extra day for jump starting needs analysis | [6 empty] | Deployment Context (1=No LMS; 2=SCORM LMS; 3=Custom LMS or Reporting) | 1 | 2 | 3
|  |  | 508 Compliance (1=yes, 0=no) |  | yes | yes | 1 |  | 2. Needs analysis – 2 days for CT, maybe focus group | [6 empty] | 508 Compliance (1=yes, 0=no) | no | yes
3. Student/Instructor pilot – we don’t know when, CT and PM, 1.5 days – may need to be there longer than just the one day in order to help facilitate feedback review
|  | Tech | [6 empty] | CT Hours | Days | Nights | OOP
|  |  | Additional Tool/Technology Dev (1-5) |  | 2 | 2 | 1 |  | 24 | 3 | 2 | 1050 |  |  |  | Additional Tool/Technology Dev (1-5) | 1 | 2 | 3 | 4 | 5
|  | Staff | [6 empty] | 24 | 3 | 2 | 1050
|  |  | Instructional Designer |  | 1 | 1 |  |  | 20 | 2.5 | 2 | 1000 |  |  |  | ID
|  |  | Senior Content Developer |  | 1 | 1 |  |  | PM Hours | [6 empty] | SCD
|  |  | Content Developer |  | 0 | 0 |  |  | 16 | 2 | 1 | 750 |  |  |  | CD
|  |  | MM Project Lead |  | 1 | 1 |  |  | 20 | 2.5 | 2 | 1000 |  |  |  | MM Lead
|  |  | MM Production |  | 1 | 1 | [9 empty] | MM Production
|  |  | Tech Project Lead |  | 1 | 1 |  |  | Airfare | 350 | [5 empty] | Tech Lead
|  |  | Tech Production |  | 0 | 0 |  |  | Per diem | 100 | [5 empty] | Tech Production
|  |  | Producer |  | 1 | 1 |  |  | Hotel | 200 | [5 empty] | Producer
|  |  | Associate Producer |  | 0 | 0 | [9 empty] | Associate Producer
|  |  | QA |  | 1 | 1 | [9 empty] | QA
|  |  | Total |  |  | 7
Assumptions
Content
|  |  |  | Research | 8 | Hours/120 segs
|  |  |  | Design | 6 | Hours/120 segs
|  |  |  | Scripting | 16 | Hours/120 segs
|  |  |  | Review | 4 | Hours/120 segs
|  |  |  | Changes | 24 | Hours/120 segs
Production rates
[6 empty] | Total cost | FTEs |  | Billable hours* |  |  |  | Cost per hour billed
|  | Department |  |  | Role | per FTE | available | 55% | 75% | 85% |  | 55% | 75% | 85%
|  |  |  | Content | C1 | 40000 | 4 | 4576 | 6240 | 7072 |  | 34.965 | 25.641 | 22.6244
[5 empty] | C2 | 55000 | 1 | 1144 | 1560 | 1768 |  | 48.0769 | 35.2564 | 31.1086
[5 empty] | C3 | 60000 | 2 | 2288 | 3120 | 3536 |  | 52.4476 | 38.4615 | 33.9367
[5 empty] | Contractor** | na | 5 | 9360 | 9360 | 9360 |  | 23.7647 | 23.7647 | 23.7647
|  |  | Sub-total |  |  |  |  | 8008 | 10920 | 12376
|  |  |  | Multimedia | MM1 | 42500 | 8 | 9152 | 12480 | 14144 |  | 37.1503 | 27.2436 | 24.0385
[5 empty] | MM2 | 50000 | 2 | 2288 | 3120 | 3536 |  | 43.7063 | 32.0513 | 28.2805
|  |  | Sub-total |  |  |  |  | 11440 | 15600 | 17680
[5 empty] | AU | 45000 | 1 | 1144 | 1560 | 1768 |  | 39.3357 | 28.8462 | 25.4525
[5 empty] | MM Contractor** | na | 2 | 3744 | 3744 | 3744 |  | 22.9412 | 22.9412 | 22.9412
|  |  |  | Technology | T1 | 50000 | 2 | 2288 | 3120 | 3536 |  | 43.7063 | 32.0513 | 28.2805
[5 empty] | T2 | 71000 | 2 | 2288 | 3120 | 3536 |  | 62.0629 | 45.5128 | 40.1584
[5 empty] | Contractor** |  | 1 |  |  |  |  | 54.1176 | 54.1176 | 54.1176
|  |  | Sub-total |  |  |  |  | 4576 | 6240 | 7072
|  |  |  | QA | QA (Contractor)** | na | 4 | 7488 | 7488 | 7488 |  | 26.4706 | 26.4706 | 26.4706
|  |  |  | Project Management | PM | 61000 | 4 | 4576 | 6240 | 7072 |  | 53.3217 | 39.1026 | 34.5023
[5 empty] | Contractor** | na | 1 | 1872 | 1872 | 1872 |  | 41.1765 | 41.1765 | 41.1765
|  | Total production hours available*** | [5 empty] | 52208 | 63024 | 68432
|  | Weighted average cost per hour (excluding contractors) | [9 empty] | 25.0153 | 20.7223 | 19.0846
[13 empty] | -17.16% | -7.903%
* Based on 40hr workweek, billable hours as a percent of total hours (total hours includes vacation, training, etc.)
** Contractor cost based on average hourly rate within each department at 85% billable utilization; High variability within Content may require additional role breakdown
*** Includes FTEs and contractors (Assumes 90% billable utilization on contractors)
Estimate of hours, role requirements, and production costs
Content
|  |  |  | Process stage | Step | Hours |  |  | Hour requirements by role |  |  | OOP |  | Production costs
[8 empty] | C1 | C2 | C3 | Contractor | Expenses |  | 75%
|  |  |  | Preparation | Pre-kickoff | 1 |  | 0% | 50% | 50% |  |  |  | 36.859
[5 empty] | Kickoff | 8 |  | 0% | 50% | 50% |  |  |  | 294.8718
[5 empty] | Post-kickoff | 1.0226 |  | 0% | 50% | 50% |  |  |  | 37.6907
[5 empty] | Content workshop | 0 |  | 0% | 100% | 0% |  |  |  | 0
[5 empty] | Needs Analysis | 90
|  |  |  | Design | Concepting | 16.8696 |  | 0% | 50% | 50% |  |  |  | 621.7975
[5 empty] | Implementation plan | 4.7818 |  | 0% | 50% | 50% |  |  |  | 176.2509
[5 empty] | Research | 11.7129 |  | 50% | 50% | 50% |  |  |  | 581.8898
[5 empty] | Prototyping | 23.1291 |  | 0% | 100% | 0% |  |  |  | 815.4504
[5 empty] | Design Doc cleanup | 7.7097 |  | 0% | 100% | 0% |  |  |  | 271.8168
[5 empty] | Release Day | 4 |  | 0% | 100% | 0% |  |  |  | 141.0256
[5 empty] | Changes | 14.4483 |  | 0% | 100% | 0% |  |  |  | 509.3937
[5 empty] | Travel | 68
|  |  |  | Alpha | Script | 85.9479 |  | 100% | 0% | 48.9% |  |  |  | 3820.1644
[5 empty] | 508 Compliance | 11.1803 |  | 100% | 0% | 0% |  |  |  | 286.6754
[5 empty] | Review | 5 |  | 0% | 0% | 100% |  |  |  | 192.3077
[5 empty] | Release Day | 6 |  | 0% | 100% | 0% |  |  |  | 211.5385
[5 empty] | Celebration | 2 |  | 0% | 50% | 100% |  |  |  | 112.1795
|  |  |  | Beta | Team meeting | 2 |  | 0% | 50% | 100%
[5 empty] | Changes | 9.6519 |  | 0% | 100% | 0% |  |  |  | 340.2926
[5 empty] | Audio script | 0.625 |  | 100% | 0% | 0% |  |  |  | 16.0256
[5 empty] | Release Day | 2 |  | 0% | 100% | 0% |  |  |  | 70.5128
|  |  |  | Final | Team meeting | 1 |  | 0% | 100% | 200% |  |  |  | 112.1795
[5 empty] | Changes | 4.826 |  | 0% | 100% | 0% |  |  |  | 170.1463
[5 empty] | Release Day | 2 |  | 0% | 100% | 0% |  |  |  | 70.5128
[5 empty] | Post-mortem | 2 |  | 0% | 50% | 100% |  |  |  | 112.1795
[5 empty] | Celebration | 2 |  | 0% | 50% | 100% |  |  |  | 112.1795
|  |  | Content Total |  |  | 386.9051 | [7 empty] | 9113.9403 | 18.93%
|  | Percent of hours in each role (Blank cells filled in to lowest role) | [5 empty] | 26.78% | 25.96% | 20.35%
|  | Percent of hours available by role | [5 empty] | 57.14% | 14.29% | 28.57%
Multimedia
|  |  |  | Process stage | Step | Hours |  |  | Hour requirements by role |  |  | OOP |  | Production costs
[8 empty] | MM1 | MM2 | AU | Contractor | Expenses |  | 75%
|  |  |  | Preparation | Pre-kickoff | 1 |  | 100% | 0% |  |  |  |  | 27.2436
[5 empty] | Kickoff | 5 |  | 100% | 0% |  |  |  |  | 136.2179
[5 empty] | Post-kickoff | 1.0226 |  | 100% | 0% |  |  |  |  | 27.8583
|  |  |  | Design | Concepting | 5.9627 |  | 50% | 50% |  |  |  |  | 176.7782
[5 empty] | Implementation plan | 2.9886 |  | 50% | 50% |  |  |  |  | 88.6044
[5 empty] | Research | 2.9282 |  | 100% | 0% |  |  |  |  | 79.7752
[5 empty] | Prototyping | 23.1291 |  | 50% | 50% |  |  |  |  | 685.7197
[5 empty] | Storyboard clean-up | 7.7097 |  | 50% | 50% |  |  |  |  | 228.5732
[5 empty] | GUI Mock-up | 9 |  | 50% | 50% |  |  |  |  | 266.8269
[5 empty] | Release Day | 4 |  | 50% | 50% |  |  |  |  | 118.5897
[5 empty] | Changes | 10.3202 |  | 50% | 50% |  |  |  |  | 305.967
|  |  |  | Alpha | Visual media assets | 6 |  | 100% | 0% |  |  |  |  | 163.4615
[5 empty] | GUI Hook-up | 5.5 |  | 100% | 0% |  |  |  |  | 149.8397
[5 empty] | Clips | 113.4272 |  | 100% | 0% |  |  |  |  | 3090.1633
[5 empty] | Interactivity Development | 20.8006 |  | 40% | 60% |  |  |  |  | 626.6839
[5 empty] | 508 Compliance | 2.2361 |  | 100% | 0% |  |  |  |  | 60.9185
[5 empty] | Review | 5 |  | 50% | 50% |  |  |  |  | 148.2372
[5 empty] | Release Day | 8 |  | 50% | 50% |  |  |  |  | 237.1795
[5 empty] | Celebration | 4 |  | 100% | 0% |  |  |  |  | 108.9744
|  |  |  | Beta | Team meeting | 2 |  | 100% | 0% |  |  |  |  | 54.4872
[5 empty] | Changes | 9.6519 |  | 50% | 50% |  |  |  |  | 286.1552
[5 empty] | Audio synch | 11.25 |  | 100% | 0% |  |  |  |  | 306.4904
[5 empty] | Release Day | 6 |  | 50% | 50% |  |  |  |  | 177.8846
|  |  |  | Final | Team meeting | 1 |  | 100% | 0% |  |  |  |  | 27.2436
[5 empty] | Changes | 4.826 |  | 50% | 50% |  |  |  |  | 143.0776
[5 empty] | Release Day | 6 |  | 50% | 50% |  |  |  |  | 177.8846
[5 empty] | Post-mortem | 2 |  | 100% | 0% |  |  |  |  | 54.4872
[5 empty] | Celebration | 2 |  | 100% | 0% |  |  |  |  | 54.4872
|  |  | Multimedia Total |  |  | 282.7528 | [7 empty] | 8009.8098 | 16.64%
|  | Percent of hours in each role (Blank cells filled in to lowest role) | [5 empty] | 77.45% | 22.55%
|  | Percent of hours available by role | [5 empty] | 80% | 20%
Audio Production
[5 empty] | Prep | 1.5 |  |  |  | 100% |  |  |  | 43.2692
|  |  |  | Beta | Record / Edit | 27 |  |  |  | 100% |  |  |  | 778.8462
|  |  |  | Final | Revisions | 5.5 |  |  |  | 100% |  |  |  | 158.6538
[5 empty] | Talent Cost |  |  |  |  | 100% |  | 2475 |  | 2475
[5 empty] | Music | 12.5 |  |  |  | 100% |  | 250 |  | 610.5769
[5 empty] | Sound Design | 25 |  |  |  | 100% |  |  |  | 721.1538
|  |  | Audio Total |  |  | 71.5 | [7 empty] | 4787.5 | 9.943%
Image Acquisition
|  |  |  | Photoshoot | Casting/Scheduling | 4 |  |  |  | 100% |  |  |  | 115.3846
[5 empty] | Shoot | 8 |  |  |  | 100% |  |  |  | 230.7692
[5 empty] | Keying/Color Correct | 1.25 |  |  |  | 100% |  |  |  | 36.0577
[5 empty] | Photographer | oop --> | [5 empty] | 650 |  | 650
[5 empty] | Talent | oop --> | [5 empty] | 1200 |  | 1200
[5 empty] | Location | oop --> | [5 empty] | 0 |  | 0
[5 empty] | Makeup | oop --> | [5 empty] | 600 |  | 600
[5 empty] | Food | oop --> | [5 empty] | 0 |  | 0
|  |  |  | Other (illustrations or purchased stock photos) | Other images | oop --> | [5 empty] | 0 |  | 0
|  |  |  | Photoshoot Total |  | 13.25
[14 empty] | 2832.2115 | 5.882%
Technology
|  |  |  | Process stage | Step | Hours |  |  | Hour requirements by role |  |  | OOP |  | Production costs
[8 empty] | T1 | T2 |  | Contractor | Expenses |  | 25%
|  |  |  | Preparation | Feasibility study | 2 |  | 50% | 50% |  |  |  |  | 232.6923
[5 empty] | Pre-kickoff | 0.5 |  | 50% | 50% |  |  |  |  | 58.1731
[5 empty] | Kickoff | 1 |  | 50% | 50% |  |  |  |  | 116.3462
[5 empty] | Post-kickoff | 0.51128 |  | 50% | 50% |  |  |  |  | 59.4858
|  |  |  | Design | Concepting | 3.9627 |  | 50% | 50% |  |  |  |  | 461.0429
[5 empty] | Implementation plan | 2.3909 |  | 50% | 50% |  |  |  |  | 278.1698
[5 empty] | Deployment analysis | 2.4401 |  | 50% | 50% |  |  |  |  | 283.8918
[5 empty] | GUI hook-up | 4 |  | 50% | 50% |  |  |  |  | 465.3846
[5 empty] | Revisions | 0 |  | 50% | 50% |  |  |  |  | 0
[5 empty] | Release Day | 1 |  | 50% | 50% |  |  |  |  | 116.3462
|  |  |  | Alpha | Interactivity templates | 14.3361 |  | 50% | 50% |  |  |  |  | 1667.9558
[5 empty] | Custom interactivity | 13.4933 |  | 50% | 50% |  |  |  |  | 1569.8931
[5 empty] | Custom tool development | 4 |  | 50% | 50% |  |  |  |  | 465.3846
[5 empty] | 508 Compliance | 44.7214 |  | 100% | 0% |  |  |  |  | 4300.1307
[5 empty] | Deployment contact | 1.22 |  | 50% | 50% |  |  |  |  | 141.9459
[5 empty] | Deployment release | 1 |  | 50% | 50% |  |  |  |  | 116.3462
[5 empty] | Release Day | 2
[5 empty] | Celebration | 1 |  | 50% | 50% |  |  |  |  | 116.3462
|  |  |  | Beta | Team meeting | 1 |  | 50% | 50% |  |  |  |  | 116.3462
[5 empty] | Changes | 1.9304 |  | 50% | 50% |  |  |  |  | 224.5931
[5 empty] | Custom tool integration | 2 |  | 50% | 50% |  |  |  |  | 232.6923
[5 empty] | Revised deploy. Proof | 1.22 |  | 50% | 50% |  |  |  |  | 141.9459
[5 empty] | Release Day | 2 |  | 50% | 50% |  |  |  |  | 232.6923
|  |  |  | Final | Team meeting | 0.5 |  | 50% | 50% |  |  |  |  | 58.1731
[5 empty] | Release Day | 1 |  | 50% | 50% |  |  |  |  | 116.3462
[5 empty] | Build to dep. Env. | 2.5 |  | 50% | 50% |  |  |  |  | 290.8654
[5 empty] | Post-mortem | 1 |  | 50% | 50% |  |  |  |  | 116.3462
[5 empty] | Celebration | 1 |  | 50% | 50% |  |  |  |  | 116.3462
|  |  | Technology Total |  |  | 113.7262 | [7 empty] | 12095.8817 | 25.12%
|  | Percent of hours in each role (Blank cells filled in to lowest role) | [5 empty] | 68.78% | 29.46%
|  | Percent of hours available by role | [5 empty] | 50% | 50%
Quality Assurance
|  |  |  | Process stage | Step | Hours |  |  | Hour requirements by role |  |  | OOP |  | Production costs
[8 empty] | QA |  |  | Contractor | Expenses |  | 90%
|  |  |  | Preparation | Pre-kickoff | 0.5 |  |  |  |  | 100% |  |  | 13.2353
[5 empty] | Kickoff | 1 |  |  |  |  | 100% |  |  | 26.4706
[5 empty] | Post-kickoff | 0.51128 |  |  |  |  | 100% |  |  | 13.534
|  |  |  | Design | Implementation plan | 2.3909 |  |  |  |  | 100% |  |  | 63.288
[5 empty] | Style guide | 2.7281 |  |  |  |  | 100% |  |  | 72.2137
[5 empty] | Prototype/DD review | 6 |  |  |  |  | 100% |  |  | 158.8235
[5 empty] | Release Day | 1.3 |  |  |  |  | 100% |  |  | 34.4118
|  |  |  | Alpha | Review script | 6 |  |  |  |  | 100% |  |  | 158.8235
[5 empty] | Review Alpha | 6.8733 |  |  |  |  | 100% |  |  | 181.941
[5 empty] | Release Day | 3 |  |  |  |  | 100% |  |  | 79.4118
[5 empty] | Celebration | 1 |  |  |  |  | 100% |  |  | 26.4706
|  |  |  | Beta | Team meeting | 1.3 |  |  |  |  | 100% |  |  | 34.4118
[5 empty] | Review audio script | 1.5 |  |  |  |  | 100% |  |  | 39.7059
[5 empty] | Review Beta | 7.9308 |  |  |  |  | 100% |  |  | 209.9319
[5 empty] | Release Day | 2 |  |  |  |  | 100% |  |  | 52.9412
|  |  |  | Final | Team meeting | 0.5 |  |  |  |  | 100% |  |  | 13.2353
[5 empty] | Review audio script | 0.75 |  |  |  |  | 100% |  |  | 19.8529
[5 empty] | Review Final | 7.402 |  |  |  |  | 100% |  |  | 195.9365
[5 empty] | Release Day | 1.5 |  |  |  |  | 100% |  |  | 39.7059
[5 empty] | Post-mortem | 1 |  |  |  |  | 100% |  |  | 26.4706
[5 empty] | Celebration | 1 |  |  |  |  | 100% |  |  | 26.4706
|  |  | QA Total |  |  | 56.1864 | [7 empty] | 1487.2862 | 3.089%
Project Management
|  |  |  | Process stage | Step | Hours |  |  | Hour requirements by role |  |  | OOP |  | Production costs
[8 empty] | PM |  |  | Contractor | Expenses |  | 75%
|  |  |  | Preparation | Organize team | 0.35 |  | 100% | [5 empty] | 13.6859
[5 empty] | Project set-up | 0 |  | 100% | [5 empty] | 0
[5 empty] | What we know doc | 2.2361 |  | 100% | [5 empty] | 87.436
[5 empty] | Pre-kickoff | 0.5 |  | 100% | [5 empty] | 19.5513
[5 empty] | Kickoff | 4 |  | 100% | [5 empty] | 156.4103
[5 empty] | Meeting notes | 1.5157 |  | 100% | [5 empty] | 59.2684
[5 empty] | Post-kickoff | 0.51128 |  | 100% | [5 empty] | 19.9925
[5 empty] | Project plan | 13.6004 |  | 100% | [5 empty] | 531.8104
[5 empty] | Travel | 36
|  |  |  | Design | Concepting | 3.9627 |  | 100% | [5 empty] | 154.951
[5 empty] | Implementation plan | 2.3909 |  | 100% | [5 empty] | 93.4896
[5 empty] | Coordination | 10.3769 |  | 100% | [5 empty] | 405.7642
[5 empty] | Client communication | 5.3078 |  | 100% | [5 empty] | 207.5498
[5 empty] | Release Day | 4 |  | 100% | [5 empty] | 156.4103
|  |  |  | Alpha | Coordination | 17.2949 |  | 100% | [5 empty] | 676.2736
[5 empty] | Client communication | 5.3078 |  | 100% | [5 empty] | 207.5498
[5 empty] | 508 Compliance | 6.1035 |  | 100% | [5 empty] | 238.6631
[5 empty] | Release Day | 6 |  | 100% | [5 empty] | 234.6154
[5 empty] | Celebration | 1 |  | 100% | [5 empty] | 39.1026
|  |  |  | Beta | Team meeting | 1 |  | 100% | [5 empty] | 39.1026
[5 empty] | Change reqs in JIRA | 2.58 |  | 100% | [5 empty] | 100.8864
[5 empty] | Coordination | 6.9179 |  | 100% | [5 empty] | 270.5095
[5 empty] | Client communication | 5.3078 |  | 100% | [5 empty] | 207.5498
[5 empty] | Release Day | 4 |  | 100% | [5 empty] | 156.4103
|  |  |  | Final | Team meeting | 0.5 |  | 100% | [5 empty] | 19.5513
[5 empty] | Change reqs in JIRA | 0.51601 |  | 100% | [5 empty] | 20.1773
[5 empty] | Coordination | 3.459 |  | 100% | [5 empty] | 135.2547
[5 empty] | Client communication | 5.3078 |  | 100% | [5 empty] | 207.5498
[5 empty] | Release Day | 4 |  | 100% | [5 empty] | 156.4103
[5 empty] | Post-mortem | 2 |  | 100% | [5 empty] | 78.2051
[5 empty] | Celebration | 1 |  | 100% | [5 empty] | 39.1026
Other
[5 empty] | Team Events (includes SB days) | oop --> | [5 empty] | 240 |  | 240
[5 empty] | Travel | oop --> | [5 empty] | 4850 |  | 4850
|  |  | Project Management Total |  |  | 157.0466 | [7 empty] | 9823.2334 | 20.4%
|  | Grand Total |  |  |  | 1081.3671 | [5 empty] | 10265 |  | 48149.863
Cost of sales
[8 empty] | Cost | Cost per | Allocated
| Direct sales costs |  |  |  | Hours | Role | Rate/Hr* | base*** | Prod. Hr | Costs
Direct selling expenses (e.g., travel)
Sales & Marketing time allocation
VP-Sales
Sales personnel
VP-Marketing
Marketing personnel
CEO
Other
Sales commission
Project Manager time
Content time
C2
C3
Multi-media time
M1
M2
Technology (T2) time
Total direct sales costs
Indirect sales costs
Marketing expenses
Sales expenses not allocated to wins
Sales & Marketing time not directly allocated
VP-Sales
Sales personnel
VP-Marketing
Marketing personnel
Total indirect sales costs
| Total cost of sales | [6 empty] | 750881.9 | 11.9142 | 12883.6473
* Rate per hour assumes a billable utilization of based on L98 hours (and equiv. utilization) for production personnel
and a net utilization of 80% for sales/marketing (after training and holidays)
| Overhead allocation | [9 empty] | Overhead Costs
[7 empty] | Cost | Cost per | Allocated |  | numbers from Bjorn, 1/11/08
| General overhead expenses |  |  |  | Hours | Rate/Hr** | base*** | Prod. Hr | Costs*
|  | Sr. Mgnt. (eventually charge time to sales as well) | [8 empty] | CT | 81
|  | Office | [8 empty] | MM | 83
|  | Building expenses | [8 empty] | SVP | 78
|  |  | Rent & utilities | [7 empty] | PM | 94
|  |  | Parking | [7 empty] | Tech | 88
|  |  | Other (e.g., bank charges, employee meals) | [7 empty] | QA | 71
Information technology
Time allocated from Tech. department
IT supplies and computers
|  | Overhead sub-total |  |  |  |  | 733230.1849 | 11.6341 | 12580.7788
| Target bonus pool for the year | [5 empty] | 400000 | 6.3468 | 6863.2083
| Total overhead costs | [5 empty] | 1133230.1849 | 17.9809 | 19443.9872
* Costs allocated to this project based on 75% billable hours in production
** Rate/hr assumes management available 85% of time (Other is vacation, sick leave, trainings, holidays, etc.)
*** Cost base is total cost available in the year
Margin allocation
[6 empty] | Total project | Rev/prod. | (Rev-OOP)/
| Price increment to achieve target margins of: |  |  |  | Margin charge-up | price | hour | prod hour
|  |  |  | 0% | 0 | 100442.8169 | 92.885 | 83.3924
|  |  |  | 5% | 5286.464 | 105729.2809 | 97.7737 | 88.2811
|  |  |  | 10% | 11160.313 | 111603.1298 | 103.2056 | 93.713
|  |  |  | 15% | 17725.203 | 118168.0198 | 109.2765 | 99.7839
|  |  |  | 20% | 25110.7042 | 125553.5211 | 116.1063 | 106.6137
|  |  |  | 25% | 33480.939 | 133923.7558 | 123.8467 | 114.3541
Sensitivity
| Production hours to drive profitability to zero |  |  |  | Role |  | Hours
Content
Multimedia
Technology
QA
Project Management
Note: Hours available assume all hours consumed by specific role
Note on G6: Deaton Bednar: While the new process does not require a concept doc, sometimes it is needed. Put a 1 here if the client needs a concept document
Note on G7: Deaton Bednar: This is the first visual of the end solution. Essentially it is a design document with storyboards in the GUI. Put a one if that is all that is going to be produced. Put a two if there will be a first look also
Note on L8: Deaton Bednar: This cannot be compared to the old estimate tool since the new tool is built on acutal cost and utilization data as assessed by our McKinsey consultant. It does cover all our actual costs including bonuses, R & D, etc which was formerly covered by the 25% profit margin.
Note on L9: Deaton Bednar: This is what we should try to get and is truly a profit margin. Change the quoted price and you'll see the margin change.
Note on L10: Julia Preston: This is $95/hr for Rev/hr, which is the current sales agreement, not (Rev-OOP)/hr.
Note on G12: Deaton Bednar: At Aug 18, 2006, there are 120 segments in an hour for our standard courses.
Note on G13: Deaton Bednar: One represents perfect content. Scripts are written and do not need editing. Five represents a client that says "I sort of know what we want but not sure" or "We have 15 SMEs and they don't agree".
Note on G14: Deaton Bednar: One would be something like a social skill and for a five, think of a difficult to understand topic such as the Minitab statistical software.
Note on G15: Adrian Taylor: 1 = Static graphics, illustration, or photography 2 = Simple animations 3 = Sophisticated animation
Note on G19: Adrian Taylor: 1 =pre-developed templates 2 = customizing the templates, could include some simple branching 3 = custom developed interactivities, could include more complex branching. For more details see N:\Operations\process docs\Multimedia\Multimedia process docs\InteractivityLevels
Note on G20: Adrian Taylor: 1 = not very often (every 9 - 13 segs) 2 = more often (every 5 - 9 segs) 3 = very frequently (every 2 - 4)
Note on G21: Deaton Bednar: This is just asking if we have to develop a new one or say no if we can use one they already have
Note on G23: Adrian Taylor: Will the course have several characters that each require a separate voice talent? Enter the number of additional voice talent.
Note on G24: Allison Dunavant: This is for stock music only. Up to 2 stock music selections. Consult David for any additional or custom music costs.
Note on G25: Deaton Bednar: Put yes, if you want sound effects, and actual design thought to create a realistic sounding solution. Think birds chirping in an outdoor restaurant scene. Consult with David if the course is to have a large sound design component.
Note on G26: Deaton Bednar: One is the client who gets it, is prepared, knows what they want and lets us do our job. Five is the client who has to have a lot of hand holding or could be a client who is not reacheable and yet demanding.
Note on G27: Deaton Bednar: This is hours. Team prep and psst meeting time is automatically figured into this.
Note on G29: Deaton Bednar: When possible, if the content is in dissary, they would benefit from upfront instructional design or strategy. This should happen before the project gets officially kicked off. The appropriate design should drive everything else.
Note on G31: Deaton Bednar: If this is a governmental agency or federal funds, they answer probably should be yes.
Note on G36: Jason Craft: - Federated wants us to write learner progress to a text file on the user's computer. That's about a 2. - Capital One's calculation spreadsheet (I think it was for Structdeal) would be a 3 to 3.5. - Lilly's spreadsheet wizard tool for the course, as originally scoped, was a 5. - The "Tamagotchi" we proposed for the Nurses Association (I can't remember the name of the client exactly) would be around a 5.
Note on E37: Allison Dunavant: This staffing is representative of a 120 segment course in a timeperiod representative of: Level 1: 10 Weeks Level 2: 14 Weeks Level 3: 16 Weeks Do Not Adjust without speaking with track lead
Note on G42: Adrian Taylor: This is the number of MM team members that will work under the lead. Large projects or projects that have tight deadlines will require additional staff, this reduces efficiency increasing cost.
Note on G44: Deaton Bednar: This is the number of tech people who will work under the tech project lead
Note on G45: Deaton Bednar: Put one here if you have a zero at associate producer or if the project consists of more than 20 hours of content. Then you may have one of each.
Note on G46: Deaton Bednar: Put a zero here if you have a producer. Put a one here if it is a very small, simple project. Not a new client. Or you may put a one here if the project has more than 20 hours of content to be deliveree and you have a producer.
Note on G47: Deaton Bednar: This should always be one unless the project is 20 hours or more of final content to be delivered
Note on G50: Deaton Bednar: I wouldn't change these with out talking to the director of the department.
Note on I63: Author: Includes average salary, benefits, and payroll expenses; all figures rounded up

## Sheet3
SampleProjects

## Test Data
Assumptions |  | Projects
1 | NewEstimate | AHA: Instructor | AHA: orientation | Canon: B&W | Canon: Techsales | CapOne: NPV | CapOne: PacDeal | Clorox: Process | ECI: SocDev | Effective Edge: Refresher | Flashvue: Video Interview | ISD: Advanstar | KLA: MyTime | Minitab: QT | Orbis: Clinical Management | Orthoclear: Cert Training | Pitney: Data Security | Pitney: FlowCom | Safeguard: Bus Stationary | Safeguard: Cards | Safeguard: Envelopes | Safeguard: Laserchecks | Safeguard: Laserforms | SAP: Virtual Teams | SAP: Business One | THR: CDR | UTC: ITO | Whole Foods: DSHEA | Whole Foods: QS | CapOne:Info Security | Yahoo: FocalReview
Concept Doc |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Prototype |  | 5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 2 | 3 | 6 | 1 | 1 | 1 | 1
Alpha |  | 5 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 2 | 3 | 6 | 1 | 1 | 1 | 1
Does it require a new UI? |  | 1 | [12 empty] | yes
Does it require a photo shoot? | [10 empty] | yes
Are we doing a video? |  | 1 | [8 empty] | yes
Segments |  | 1140 | 60 | 60 | 220 | 30 | 100 | 100 | 90 | 120 | 90 | 150 | 40 | 2829 | 180 | 90 | 60 | 120 | 120 | 90 | 120 | 120 | 90 | 1200 | 130 | 280 | 1400 | 60 | 95 | 90 | 60
Content Disarray (1-5) |  | 4 | 4 | 4 | 3 | 5 | 1 | 4 | 3 | 3 | 5 | 2 | 3 | 2 | 2 | 4 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 4 | 3
Content Difficulty (1-5) |  | 3 | 2 | 2 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 4 | 1 | 5 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 4 | 2 | 2 | 2 | 2
Visual Media Level (1-3) |  | 3 | 2 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 3 | 2 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2
Interactivity Level (1-3) |  | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 1 | 1 | 1 | 1
Interactivity Frequency (1-3) |  | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1
GUI (1=Custom, 0=template) |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1
Voice Over (1=yes, 0=no) |  | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | 0 | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes
Additional Voice Talent |  | 4 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 3 | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4 | 1 | 0 | 0 | 0
Music (1=yes, 0=no) |  | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Client Difficulty (1-5) |  | 3 | 2 | 2 | 2 | 4 | 2 | 3 | 3 | 4 | 4 | 5 | 2 | 3 | 2 | 5 | 2 | 5 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 3 | 1 | 2 | 3 | 4
Kickoff length |  | 24 | 4 | 4 | 8 | 2 | 2 | 2 | 4 | 8 | 12 | 8 | 2 | 8 | 4 | 8 | 2 | 4 | 2 | 2 | 2 | 8 | 2 | 0 | 4 | 8 | 8 | 4 | 4 | 2 | 4
Kickoff Location (1=phone, 2=enspire, 3=client) |  | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 1 | 2 | 3 | 2 | 2 | 1 | 1
Special Content Workshop (enter hours here) |  | 80 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 150 | 0 | 24 | 80 | 0 | 8 | 24 | 0
Deployment Context (1=No LMS; 2=SCORM LMS; 3=Custom LMS or Reporting) |  | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Additional Tool/Technology Dev (1-5) |  | 4 | 1 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 5 | 1 | 1 | 1 | 0
508 Compliance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ID |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
SCD |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1
CD |  | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 1
MM Lead |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
MM Production |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Tech Lead |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tech Production |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Producer |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Associate Producer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total Hours | 0 | 6527.15 | 249 | 349 | 1205 | 248 | 398 | 859 | 455 | 654 | 930 | 1293 | 248 | 11121 | 597 | 711 | 323 | 987 | 301 | 211 | 256 | 633 | 326 | 4345 | 819 | 1082 | 5855 | 228 | 338 | 337 | 293
CT | 0 | 1805.15 | 138 | 88 | 376 | 94 | 41 | 214 | 131 | 246 | 74 | 283 | 43 | 4428 | 140 | 193 | 104 | 265 | 93 | 64 | 80 | 187 | 84 | 1248 | 247 | 399 | 1727 | 53 | 103 | 115 | 156
MM | 0 | 2188 | 61 | 180 | 495 | 88 | 257 | 436 | 154 | 227 | 476 | 382 | 143 | 4117 | 181 | 297 | 131 | 476 | 125 | 81 | 122 | 276 | 154 | 1927 | 387 | 439 | 1835 | 96 | 156 | 139 | 84
PM | 0 | 1721 | 36 | 46 | 127 | 44 | 63 | 115 | 82 | 115 | 275 | 427 | 35 | 1363 | 95 | 161 | 45 | 175 | 43 | 33 | 30 | 97 | 43 | 485 | 72 | 168 | 888 | 45 | 56 | 38 | 42
Tech | 0 | 257 | 0 | 22 | 155 | 16 | 14 | 46 | 63 | 21 | 53 | 162 | 19 | 297 | 140 | 39 | 16 | 34 | 18 | 7 | 4 | 47 | 15 | 507 | 34 | 97 | 1219 | 21 | 12 | 12 | 7
QA | 0 | 232 | 14 | 13 | 52 | 6 | 23 | 40 | 25 | 45 | 52 | 39 | 8 | 604 | 42 | 21 | 27 | 37 | 22 | 26 | 20 | 26 | 30 | 178 | 57 | 57 | 186 | 13 | 11 | 18 | 4
Audio | 0 | 324 | 8 | 16 | 44 | 8 | 45 | 8 | 21 | 20 | 104 | 41 | 14 | 311 | 0 | 23 | 22 | 89 | 18 | 13 | 14 | 25 | 18 | 51 | 23 | 32 | 171 | 19 | 47 | 14 | 6

## Version Notes
Version | Notes | Initial
6.4 | Added a total of 3 hours (1.5 design, 1.5 hook-up) if template GUI is used Added dollars for illustrations and photo shoots (if no photo shoot then automatic dollars for image acquisition based on visual media level
6.5 | Added sound design Removed non-functional old Photo shoot line
6.6 | Removed celebration and debrief modifier for historical projects Lowered design time from 9 hours/120 segs to 8 hours/120 segs Pricing Overview reformatted
6.7 | Add back in OOP expenses for PM Team Events and Travel
6.8 | Fixed error in OOP photographer expense. | AT
6.9 | Notes added | DB
6.9.1 | Edited 0176 (OOP for voice talent) was not scaling properly. Did not feel that this was a big enough change to go to version 7. | AT
7 | removed staffing option & custom tool configuration choice from green area | AD
7.1 | Added data for Clorox, Minitab, Orbis; amended Flashview data | NK
7.2 | Revised LMS category for new SOW language | JC
7.3 | Audio and photo OOP and hours adjusted | DC
7.4 | Added hours for photo production and adjusted sound design/music hours | DC
7.5 | Added the automatically generating line item descriptors starting at AE3 | SR
7.6 | Changed Audio sum to SVP total hours to include I194 photo hours which weren't populating anywhere in total hours before | JP
7.7 | incorporates the sum of OOP expenses into the three $/hr cells in column P | JP
7.8 | New margins based on new costs 1/11/08; outputs at the top pricing area changed to reflect margin minimums and $95/hr sales agreement; added the total oop expenses to the top box. | JP
7.9 | Added to cover greater OOP expenses for food/celebrations | JP
8 | Changed auto-populated text related to video lever | JP
8.1 | Updated low QA output error | JP